***Project Schedule***

December – Define Requirements  
 Week 1 – Finalize initial requirements doc  
 Week 2 – Communicate requirements with CCLAC volunteers, collect any feedback?  
 Define date model  
 Week 3 – Finalize data model   
 Week 4 – Christmas  
 Week 5 – New Year

January – Initial Development  
 Week 1 – Test MySQL and PHPMyAdmin setup and portability  
 Week 2 – Test VB – MySQL integration  
 Week 3 – Create and populate initial tables (req 3.2.1 and 3.2.2)  
 Week 4 – Create user table view (req 3.1.2.2)

February – Continued Development (month-long: work on long-term hosting with volunteers)  
 Week 1 – Create new record form (req 3.1.1.1)  
 Week 2 – Create Edit record form (req 3.1.1.2)  
 Week 3 – Create Public view (req 3.1.2.1)  
 Create Menu and page navigation  
 Week 4 – Finalize User and public view tables  
 Continue Page Navigation  
 Create Specific Information view for user (req 3.1.2.3)

March – Administrative Controls (month-long: work on how to test with volunteers)  
 Week 1 – Create user information table (req 3.1.2.5)  
 Week2 – Create new user page (req 3.1.1.3)  
 Week 3 – Add admin/normal user security to pages and menu (req 3.5)  
 Week 4 – Add Email Alert function (req 3.2.4)  
 Week 5 – Unit test

April – Testing  
 Week 1 – Continue unit testing  
 Create Basic User Manual  
 Week 2 – System Testing, work with CCLAC volunteers if available  
 Week 3 – Continue System Testing  
 Week 4 – Performance and Deployment Testing

May – Deployment  
 Week 1 – Perform mock recall on our system  
 Week 2 – Work with CCLAC volunteers to deploy site.   
 Week3 – Continue Deployment  
 Week 4 – Train long-term support  
 Finalize User Manual